## Proposed Roadmap
# | Group | Feature | Details / Spec | Why it matters | Size | Priority
Completes existing flows
1 |  | Sales Order | Chain: Quote → SO → Delivery Challan → Invoice. Track qty ordered / delivered / billed per line. Pending-order report. Convert at each step (like existing PO → Bill). | Estimate and PO exist but the sales side has no order stage — distributors live on pending-order tracking. | M | 1
2 |  | Batch selection on document lines | Bill in → create batch (batch no, mfg date, expiry). Invoice out → pick batch, FEFO suggested. Reports: batch-wise stock, expiring in 30/60/90 days. Items already carry Batch/Expiry flags. | Pharma / FMCG / food cannot run without line-level batches; flags exist but lines don't ask. | L | 1
3 |  | Reorder level + low-stock alerts | Reorder qty on item. Dashboard card + report 'below reorder'. One click → draft PO to the last vendor of that item. | Turns inventory from record-keeping into buying decisions. | S | 2
4 |  | GSTR-2B reconciliation | Import GSTR-2B JSON from portal → match to bills by GSTIN + invoice no + amount → buckets: Matched / In books not 2B / In 2B not books. ITC actually claimable. Bills are already server-side. | The single biggest monthly pain for any GST business; direct ITC money. | M | 1
5 |  | TDS / TCS on transactions | 194Q TDS on purchases and 206C(1H) TCS on receipts past thresholds. Per-party accumulation against the ₹50L limit, auto ledger posting, TDS/TCS payable report for challan filing. TAN already captured. | Mandatory compliance for mid-size traders; nothing computes today. | M | 2
Receivables discipline
6 |  | Payment reminders (WhatsApp/email) | Overdue invoice → reminder with PDF link. Schedule: on due date → +7 → +15 days. Start with wa.me deep link + prefilled message (zero API cost), upgrade to WhatsApp Business API later. | WhatsApp is THE collection channel for Indian SMB; extends the credit-limit work. | S | 1
7 |  | Customer statement + ageing | Party ledger as shareable PDF for a date range: opening, invoices, receipts, closing. Ageing buckets 30/60/90 alongside. | Customers and CAs ask for statements constantly. | S | 2
8 |  | PDC / cheque tracking | Post-dated cheques received/issued: due date, bank, status Pending → Deposited → Cleared / Bounced. Bounce reverses the receipt and adds charges. | Cheques still dominate B2B trade payments. | M | 3
9 |  | POS day close (Z-report) | Day's sales by tender (Cash/UPI/Card), cash denomination count, over/short, day book. Shift close. | Retail counters do not trust a POS without a day close. | S | 2
Accountant / year-end
10 |  | Tally export | Export masters + vouchers as Tally XML for any date range. | Every Indian CA asks for 'Tally data' — removes the biggest adoption objection. | M | 1
11 |  | Fixed assets + depreciation | Asset register, block-wise depreciation (Companies Act / IT Act rates), yearly depreciation JV auto-drafted. | Needed at every year-end; currently manual JVs. | M | 3
12 |  | Year-end close | FY lock, P&L → capital transfer JV, opening balances carried to new FY, posted periods frozen. | Books need a clean cut-over every April. | M | 3
13 |  | Cost centers / projects | Tag invoices and expenses to branch / project / vertical; P&L filtered by cost center. | First question from any multi-vertical owner. | M | 3
Fixes & small adds
14 |  | Warehouse-scoped opening stock | Opening qty per warehouse (today opening stock is company-wide, so warehouse-filtered stock checks read 0 for fresh items — found in testing). | Correctness fix for the negative-stock guard. | S | 2
15 |  | Barcode on items + POS scan | Barcode field on the item; POS search box accepts scanner input (keyboard-wedge) → instant add to cart. | Cheap; makes POS usable at real counters. | S | 2
16 |  | Item images | Image on item master, thumbnail in POS grid and pickers. | POS usability; catalogue feel. | S | 3
17 |  | RCM flag on purchases | Reverse-charge flag on bill → RCM liability in GSTR-3B summary. | Compliance completeness for freight / unregistered purchases. | S | 3

## Already Shipped
# | Feature | What was delivered | Status
1 | POS | Counter-sale screen under Sales: tap items, Cash/UPI/Card tender, books a PAID B2C invoice + receipt, printable slip (POS-n series). | DONE
2 | Delivery challan | DC-n series, purpose (job work / approval / own use / exhibition), vehicle no, convert-to-invoice, e-way bill JSON (docType CHL). | DONE
3 | Invoice template customization | Template + accent colour + printed Terms & Conditions; renders on invoice preview. | DONE
4 | Discount module (all 9 types) | One rules engine: item / product / category / customer / customer-group scope; percentage or fixed per unit; quantity tiers (buy 10→5%, 50→10%, 100→15%); promotional validity window; invoice-level %/₹ discount; best rule auto-applies with named toast. | DONE
5 | Other charges | Transport / reimbursement rows with own GST rate, taxed like lines, shown separately. | DONE
6 | Multiple ship-to addresses | Per customer with SHIP-n codes; Deliver-to picker on invoice; prints on the document. | DONE
7 | MRP on items | MRP field on item master. | DONE
8 | Batch / Expiry flags | Tracking type per item: None / Batch / Batch+Expiry (line-level batch pick is the roadmap item). | DONE
9 | Last selling / purchase price | Item pick prefills the party's last rate from invoices/bills with a source toast. | DONE
10 | Price lists | Named rate cards (Retail/Wholesale/…), per-item rates, per-customer assignment; resolution: price list → last paid → item master. | DONE
11 | Customer credit management | Credit limit + credit days; invoice create warns via confirm dialog on limit breach or overdue invoices. | DONE
12 | Salesman module | Master with commission %, salesman on invoice, report: invoices, pre-GST sales, commission due. | DONE
13 | Recurring invoices | Schedules from any invoice: Weekly/Monthly/Quarterly/Yearly, first-run date, end date, pause/resume, Run now; lifecycle Scheduled → Generated → Sent → Paid; draft-first generation. | DONE
14 | e-Invoice (IRP) native workflow | Create → Validate → Generate IRN → QR → Download. Stores IRN, ack no/date, signed invoice JWT, signed QR (rendered + printed), registered JSON, cancellation status. Cancel within 24h with reason codes. NIC direct (full crypto) + GSP gateway providers. | DONE
15 | e-Way Bill | Transport capture (transporter, vehicle, distance, mode, LR no/date) on invoices and challans; EWB by IRN via NIC API; EWB-01 JSON for bulk tool; EWB no + validity stored. | DONE
16 | GSTR-1 / GSTR-3B | Portal JSON export (b2b/b2cs/cdnr) + summary views. | DONE

## Build Order
Order | Feature | Reason
1 | Sales Order | Completes the sales document chain you already have on the purchase side.
2 | Batch on document lines + expiry alerts | Item flags exist; this makes them real. Opens pharma/FMCG segment.
3 | GSTR-2B reconciliation | Monthly ITC money; bills already server-side.
4 | Payment reminders (WhatsApp link first) | Touches cash collection daily; cheap first version.
5 | Tally export | Kills the CA objection to adopting Neev One.
6 | Reorder alerts + barcode + POS day close | Small items that round out retail/inventory.
7 | TDS/TCS | Compliance for larger traders.
8 | Fixed assets + year-end close + cost centers | Year-end pack — schedule before March.