## RBAC E2E (19 Aug 2026)
# | Area | Test performed | Expected | Observed | Result
Server test suite
1 |  | Full vitest suite incl. permissions, default roles, auth hardening, RBAC on all routes | 209 tests pass | 20 files, 209/209 passed | PASS
Roles
2 |  | Default roles seeded on the org | Owner, Administrator, Accountant, Sales User, Store Keeper, Viewer present with descriptions | All six listed on Settings → Roles | PASS
3 |  | Create custom role via Roles page | Role saved with selected permission checkboxes | 'QA Test Role' created; appears in role lists and user form | PASS
Users
4 |  | Create user with role + branch scope | User created with temp password, role select (incl. '+ Create new role…'), All-branches / per-branch checkboxes | 'Sales Clerk' (clerk.qa@example.com) created with Sales User role, all branches | PASS
5 |  | Sign in as the new user | Login works with temp password | Logged in; email-verification banner shown (expected, no SMTP) | PASS
UI trimming (as Sales Clerk)
6 |  | Sidebar reflects role permissions | Sales modules visible; Purchases, Cash & Bank, Journal Entries, Chart of Accounts, Vendors, admin Settings hidden | Exactly that: Sales/Inventory-view/Customers/Items/Reports only; Settings shows just My Profile | PASS
API enforcement (as Sales Clerk)
7 |  | GET /invoices | 200 (SALES view granted) | 200 | PASS
8 |  | GET /customers | 200 (MASTERS Customers view) | 200 | PASS
9 |  | GET /bills | 403 | 403 | PASS
10 |  | GET /vendors | 403 | 403 | PASS
11 |  | GET /users | 403 | 403 | PASS
12 |  | GET /roles | 403 | 403 | PASS
13 |  | GET /ledger/trial-balance | 403 | 403 | PASS
14 |  | POST /bills (forbidden write) | 403 | 403 — server blocks the write, not just the UI | PASS
Allowed workflow (as Sales Clerk)
15 |  | Create an invoice end to end | Clerk can raise a sales invoice | BUG then PASS — first attempt impossible: warehouse list 403 (preset gap, see Bugs sheet). After fix: invoice created successfully with server-hydrated customers | BUG→FIXED
Role Permissions matrix (as Owner)
16 |  | Grant 'Company, Branch & Warehouse → View' to Sales User | PUT saves; clerk gains access | PUT 200; clerk's warehouses call went 403 → 200 with 3 warehouses, live, without re-login | PASS
Session integrity
17 |  | Owner → clerk → owner session swap | Owner session restored fully | Admin sidebar + permissions back; stale profile-chip email corrected (userEmail cache) | PASS

## Bugs Found & Fixed
# | Severity | Bug | Root cause | Fix | Commit | Status
1 | High | Sales User (and Store Keeper) could not complete ANY invoice/stock form — Warehouse dropdown empty, save silently blocked | Role presets lacked MASTERS · Company/Branch setup · VIEW, so the branches/warehouses list APIs returned 403; the mandatory warehouse select had no options and native validation blocked submit with no message | Presets now grant the read for future orgs; existing orgs: one tick on Role Permissions → 'Company, Branch & Warehouse' → View (verified live — took effect without re-login) | 4a36335 | FIXED
2 | Low | 'IRP auto-registration failed: Permission denied' toast on every invoice created by a non-admin when e-invoice auto-register is on | The auto-register path reads the e-invoice gateway settings, which needs the settings permission; the 403 surfaced as an error toast although the invoice saved fine | Settings read is now opportunistic — no permission → skip auto-registration silently | 4a36335 | FIXED

## Business-Flow E2E Coverage
# | Flow | Verified behaviour | Where tested
1 | Sales: invoice → receipt | Create, GST math (line/invoice discounts, other charges, 28%/18% split), receipt with advance | localhost + tunnel
2 | Purchases: PO → bill → payment | PO create, convert to bill, payment with advance; number-collision handled with clear message | localhost
3 | Credit / debit notes | Server write-through (201) with backendDocId; stock guard on returns | localhost
4 | Sales Orders | SO → challan → invoice chain; Ordered/Delivered/Billed 5/0/0 → 5/5/0 → 5/5/5; pending filter | localhost
5 | Delivery challans | DC create, purpose codes, convert-to-invoice flips status only on successful save; EWB JSON docType CHL | localhost + tunnel
6 | Batch tracking | Bill-in creates batch (mandatory, validated pre-server); FEFO auto-pick on invoice; over-stock block; report in/out/balance 20/5/15; expiry chips | localhost
7 | POS | Barcode scan-to-cart (Enter clears box), sale books PAID invoice + receipt server-side, day close with denomination count and over/short ₹3.74 exact | localhost + tunnel
8 | Discount rules (9 types) | Item 7%, fixed ₹10/unit, category 8%, customer 12%, qty tiers 5/10/15%, expired promo correctly inert; best-rule-wins with named toasts | localhost + tunnel
9 | Price lists | Wholesale ₹999 resolved on invoice with source toast; assignment per customer | localhost + tunnel
10 | Credit management | Limit-breach confirm dialog with exact figures; overdue warnings; Create-anyway override | localhost + tunnel
11 | Recurring invoices | Schedule from invoice, frequencies, due periods materialise as drafts, lifecycle Scheduled→Generated, pause/resume | localhost + tunnel
12 | Payment reminders | Due→+7→+15 stages, wa.me link with 91-prefixed mobile and full message, history stamp, Send-now clears | localhost
13 | e-Invoice workflow | Validate (B2C + HSN caught, button gated) → Generate IRN (gateway path fires) → QR render → downloads; cancel API tested via stub NIC crypto; 24h window enforced server-side | localhost + tests
14 | e-Way bill | Transport form (transporter/vehicle/distance/mode/LR) on invoices + challans; JSON verified field-by-field | localhost + tunnel
15 | GSTR-1 / 3B / 2B | GSTR-1 portal JSON valid (b2b/b2cs/cdnr); 3B figures; 2B recon: 4 buckets exact incl. diff ₹1,504.65 pinned to its bill | localhost
16 | Tally export | 172 ledger masters + 322 vouchers, valid XML, every voucher sums to zero | localhost
17 | TDS/TCS | 194Q per-vendor excess ₹125.71 exact; 206C on receipts ₹39.40; balanced 13-line JE draft | localhost
18 | Fixed assets / FY close / cost centers | WDV ₹1,02,000 + half-rate ₹20,000 exact; closing JV; year lock refused back-dated invoice; CC P&L attributed tagged income | localhost
19 | Reorder alerts | 15 ≤ level 50 → suggest 85; draft PO to last vendor, server-numbered | localhost
20 | Inventory transfers / journals / cash-bank | WT-1, BT-1, balanced JE-1, bank txn + auto knock-off receipt | localhost
21 | Reports hub | TB ledger drill + CSV/Sheet, P&L, BS, Cash Flow with real figures | localhost
22 | Settings | Branches, warehouses, users, roles, features toggle, tax & compliance, GST rates + auto-ledger | localhost + tunnel